## Gantt Chart
AlgoNova - AI-Powered Data Structures, Algorithms and System Design Platform - SDG-4
React + Vite + Node.js + MongoDB ¦ A.Y. 2026-2027
PROJECT TIMELINE — GANTT CHART
AlgoNova - AI-Powered Data Structures, Algorithms and System Design Platform - SDG-4
Activity | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11
Problem Identification & Literature Survey | ✔ Done
Requirement Gathering & Analysis | ✔ Done
Abstract Preparation & Submission | ✔ Done
SRS Documentation | ✔ Done
System Architecture & Database Design (MongoDB Schema, REST API Design) | Pending
UI/UX Wireframing & Dashboard Screen Flow (React + Tailwind + Brutalist Theme) | Pending
Module 1: Authentication & User Profile (JWT, Google OAuth, Streak System) | Pending
Module 2: Algorithm Visualizer (Sorting, Searching, Trees, Graphs, Heap) | Pending
Module 3: Code Tracer & Multi-Language Support (JS, Python, C++, Java) | Pending
Module 4: Algorithm Race Mode (Side-by-side comparison with live stats) | Pending
Module 5: Practice Arena & Code Editor (Monaco Editor, Judge0 API) | Pending
Module 6: AI Interview Prep (Speech-to-Text, Gemini AI Feedback) | Pending
Module 7: Resume Screener (PDF Parsing, AI ATS Analysis) | Pending
Module 8: System Design Sandbox (Excalidraw Integration) | Pending
Module 9: Leaderboard & Gamification (XP, Badges, Global Ranking) | Pending
Integration & System Testing | Pending
Deployment (Vercel + Render + Docker) | Pending
Documentation & Final Report | Pending
Presentation / Demo Preparation | Pending
Legend: |  |  | Completed
Upcoming / Pending
Weeks 1–4: Problem Identification, Requirement Gathering, Abstract Submission, SRS Documentation, and System Architecture — completed.
Weeks 4–9: Full-stack development (Auth, Visualizer, Code Tracer, Race Mode, Practice Arena, AI Interview, Resume Screener, Leaderboard) — completed.
Weeks 9–11: Integration testing, deployment (Vercel/Render/Docker), final documentation, and demo preparation — pending.